## Sheet1
SavePlate – Smart Food Waste Reduction Web App
Work Breakdown Structure (WBS) – Assignment 1, Task 1
Resource Allocation
|  | Activity / Tasks | Milestone / Deliverable | Duration (hours) | Duration (days) | Precedence | Sujina Tuladhar | Pasang Lama
| 1 | Planning
1.1 |  | Determine Project Title |  | 0.5 | 1 | NIL | 100 | 100
1.2 |  | Write the Overview |  | 1 | 1 | NIL | 100 | 0
1.3 |  | Write Aims and Objectives |  | 1 | 1 | NIL | 0 | 100
1.4 |  | Write the Scope |  | 1 | 1 | 1.3 | 100 | 0
1.5 |  | Project Schedule |  |  |  | 1.4
| 1.5.1 | Derive WBS |  | 2 | 1 | NIL | 100 | 100
| 1.5.2 | Determine Milestones/ Deliverables |  | 1 | 1 | 1.5.1 | 100 | 100
| 1.5.3 | Derive Gantt Chart |  | 2 | 1 | 1.5.2 | 100 | 100
1.6 |  | Gantt Chart File (.gan) | Milestone / Deliverable |  | 1 | 1.5.3 | 100 | 100
1.7 |  | Derive technical Platform Description |  | 2 | 1 | NIL | 100 | 100
1.8 |  | Derive Risk Management Plan |  | 2 | 1 | NIL | 100 | 100
1.9 |  | Project Proposal/ Plan (.docx) | Milestone / Deliverable |  |  | 1.8 | 100 | 100
| 2 | Requirements
2.1 |  | Determine Functional and Non Functional Requirements |  | 4 |  | NIL | 100 | 100
2.2 |  | Modelling Requirements (User Stories and Acceptance Citeria) |  |  |  | 2.1
| 2.2.1 | Register User and privacy settings |  | 3 |  | NIL | 100 | 0
| 2.2.2 | Manage Food Inventory |  | 3 |  | NIL | 0 | 100
| 2.2.3 | Browse Food Items |  | 3 |  | NIL | 100 | 0
| 2.2.4 | Food Analytics |  | 3 |  | NIL | 100 | 0
| 2.2.5 | View Notifications |  | 3 |  | NIL | 0 | 100
| 2.2.6 | Plan Weekly meals |  | 3 |  | NIL | 0 | 100
| 3 | Design
3.1 |  | Design UX / wireframes (Figma) |  |  |  | 2.2
| 3.1.1 | Wireframe – Register User, Browse Food & Food Analytics |  | 4 |  | NIL | 100 | 0
| 3.1.2 | Wireframe – Manage Inventory, Notifications & Meal Planner |  | 4 |  | NIL | 0 | 100
3.2 |  | Design Site Map |  | 2 |  | 3.1 | 100 | 100
3.3 |  | Design Architectural Diagram |  | 2 |  | 3.1 | 100 | 100
3.4 |  | Design database |  |  |  | 3.2
| 3.4.1 | Design ERD |  | 3 |  | NIL | 100 | 100
| 3.4.2 | Design Data Dictionary |  | 3 |  | 3.4.1 | 100 | 100
3.5 |  | Requirements Specification and Design document | Milestone / Deliverable |  |  | 3.4 | 100 | 100
| 4 | Iteration 1 Development
4.1 |  | Coding & Testing – Register User & Privacy Settings |  |  |  | NIL | 100 | 0
4.2 |  | Working Webpages – Register User | Milestone / Deliverable |  |  | 4.1 | 100 | 0
4.3 |  | Coding & Testing – Browse Food Items |  |  |  | 4.2 | 100 | 0
4.4 |  | Working Webpages – Browse Food Items | Milestone / Deliverable |  |  | 4.3 | 100 | 0
4.5 |  | Coding & Testing – Food Analytics |  |  |  | 4.4 | 100 | 0
4.6 |  | Working Webpages – Food Analytics | Milestone / Deliverable |  |  | 4.5 | 100 | 0
4.7 |  | Coding & Testing – Manage Food Inventory |  |  |  | NIL | 0 | 100
4.8 |  | Working Webpages – Manage Food Inventory | Milestone / Deliverable |  |  | 4.7 | 0 | 100
4.9 |  | Coding & Testing – View Notifications |  |  |  | 4.8 | 0 | 100
4.1 |  | Working Webpages – View Notifications | Milestone / Deliverable |  |  | 4.9 | 0 | 100
4.11 |  | Coding & Testing – Plan Weekly Meals |  |  |  | 4.1 | 0 | 100
4.12 |  | Working Webpages – Plan Weekly Meals | Milestone / Deliverable |  |  | 4.11 | 0 | 100
4.13 |  | Integration Testing |  |  |  | 4.12 | 100 | 100
4.14 |  | Functional Testing |  |  |  | 4.13 | 100 | 100
4.15 |  | Finalise Design & Testing Document |  |  |  | 4.14 | 100 | 100
4.16 |  | Iteration 1 Prototype Demo & Presentation | Milestone / Deliverable |  |  | 4.15 | 100 | 100
| 5 | Iteration 2 Development
| 5.1 | Continue Coding & Bug Fixing (both members) |  |  |  | 4.16 | 100 | 100
| 5.2 | Test Analysis Report & Screenshots |  |  |  | 5.1 | 100 | 100
| 5.3 | Project Review & Reflection (individual) |  |  |  | 5.2 | 100 | 100
| 5.4 | Gantt Chart Comparison (Baseline vs Actual) |  |  |  | 5.3 | 100 | 100
| 5.5 | Final Demo & Presentation | Milestone / Deliverable |  |  | 5.4 | 100 | 100